# ImLab - Module-wise Plan and Timeline

## How to Build Each Module, With Durations and Milestones

Version: 1.0 | Team assumed: 2 .NET, 2 Angular, 1 UI/UX, 1 QA, 1 BA/PO, part-time DevOps and PM | Sprint length: 2 weeks

## 1. Timeline at a Glance

Total: 40 weeks (about 9 months) plus 4 weeks buffer = 44 weeks (about 10 months). MVP (a lab can register, bill, collect samples, enter and authorize results and print reports) is ready at week 27.

| Phase | Module group | Weeks | Duration | Depends on |
| --- | --- | --- | --- | --- |
| 0 | Discovery, UX design, architecture | W1-W3 | 3 wks | - |
| 1 | Platform foundation (multi-tenancy, auth, config engine, UI shell) | W4-W9 | 6 wks | Phase 0 |
| 2 | Masters and charges | W10-W15 | 6 wks | Phase 1 |
| 3 | Registration, billing, patient search | W14-W19 | 6 wks | Phase 2 (tests, charges) |
| 4 | Sample flow, result entry, authorization | W18-W24 | 7 wks | Phase 3 |
| 5 | Report printing, delivery, signatures | W23-W27 | 5 wks | Phase 4 |
| 6 | Referral, corporates, outsource, complement | W24-W27 | 4 wks | Phase 3 |
| 7 | Dashboard, MIS and other reports | W27-W31 | 5 wks | Phases 3-6 |
| 8 | Machine integration | W28-W31 | 4 wks | Phase 4 |
| 9 | SaaS admin: plans, subscriptions, tenant portal | W32-W35 | 4 wks | Phase 1 |
| 10 | Hardening, UAT, data import, go-live | W36-W40 | 5 wks | All |
| - | Buffer | W41-W44 | 4 wks | - |

## 2. Milestones

| Milestone | Week | Exit criteria |
| --- | --- | --- |
| M0 Design signed off | W3 | Clickable prototype, design system, architecture and DB design approved |
| M1 Platform demo | W9 | Create a tenant from the admin console; its own database is created and seeded; tenant login works; a config change changes UI behavior |
| M2 Masters and billing | W19 | Tests, packages, charges set up; a patient can be registered and billed with payments and receipts |
| M3 MVP | W27 | End-to-end flow from registration to printed report with signature, role permissions in place |
| M4 Feature complete | W35 | All modules and reports, machine integration, subscriptions |
| M5 Go-live | W40 | UAT passed, security test done, backups verified, first tenants migrated |

## 3. Sprint Calendar

| Sprint | Weeks | Focus |
| --- | --- | --- |
| S0 | W1-W2 | Requirements workshops, UX wireframes |
| S1 | W3-W4 | Design system, architecture, repo and CI/CD setup |
| S2 | W5-W6 | Master DB, tenant resolution, provisioning job |
| S3 | W7-W8 | Config engine, auth, roles, UI shell |
| S4 | W9-W10 | Migration runner, platform admin basics, demo; start masters |
| S5 | W11-W12 | Departments, specimen types, units, tests (basic) |
| S6 | W13-W14 | Test parameters/ranges, templates, packages |
| S7 | W15-W16 | Charges, price lists, referral doctors, centers; start registration |
| S8 | W17-W18 | Registration form and billing |
| S9 | W19-W20 | Patient search, view drawer, payments, refunds; start samples |
| S10 | W21-W22 | Sample status, barcode, result dashboard |
| S11 | W23-W24 | Result entry, ranges, authorization; start report PDF |
| S12 | W25-W26 | Report PDF, signatures, delivery by email/WhatsApp; corporates, outsource |
| S13 | W27-W28 | MVP hardening; MIS reports begin; machine bridge begins |
| S14 | W29-W30 | Reports batch 1 and 2, machine mapping |
| S15 | W31-W32 | Reports batch 3, dashboard widgets; SaaS plans |
| S16 | W33-W34 | Subscriptions, invoices, tenant self-service |
| S17 | W35-W36 | Performance and security hardening |
| S18 | W37-W38 | UAT with pilot labs, fixes |
| S19 | W39-W40 | Data import tools, go-live, handover |

## 4. Module-wise Plan

For every module, the work follows the same order: (1) DB migration and seed, (2) API with validation and permission keys, (3) unit and integration tests, (4) Angular screens from the approved design, (5) config hooks, (6) QA and fixes, (7) demo and sign-off.

### Phase 0 - Discovery and Design (W1-W3)

| Step | Work | Output |
| --- | --- | --- |
| 1 | Workshops on lab flows, review the reference screens, list all screens and fields | Screen inventory (about 45 screens) |
| 2 | Wireframes and a new visual identity: color palette, typography, icon set, left-sidebar layout, grid, form and drawer patterns | Design system, clickable prototype |
| 3 | Architecture: tenancy, config model, security, API conventions, folder structure, naming | Architecture document |
| 4 | Database design for master and tenant; migration tooling choice | ERD and scripts layout |
| 5 | Environments, repos, CI/CD, coding standards | Pipeline running on an empty skeleton |

### Phase 1 - Platform Foundation (W4-W9, 6 weeks)

| Sub-module | How to build | Weeks |
| --- | --- | --- |
| Master DB and tenant registry | Create imlab_master tables (tenants, tenant_databases, plans, platform_users, migration_history, config). Encrypt connection strings. | 1 |
| Tenant resolution | Middleware reads sub-domain, loads tenant (cached), sets a scoped DbContext with that connection; reject unknown or suspended; add tenant claim to JWT. | 1 |
| Provisioning job | Background job: create database, run baseline migration, seed roles, permissions, departments, specimen types, units, number series, default center, config defaults, first admin; write status log. | 1.5 |
| Migration runner | Versioned SQL/EF scripts, per-tenant version table, run for all tenants, failure report, retry. | 1 |
| Config engine | One config table; seed registry of keys with type, control, validation; resolver (user > tenant > platform); cache with invalidation; read and admin APIs; Angular config service and a generated settings page. | 1.5 |
| Auth, users, roles, permissions | Login, refresh, lockout, role CRUD, permission matrix by permission keys, authorization policies, logout-all, audit. | 1.5 |
| Angular shell | Left sidebar from config and permission, top bar with global search, theme from config, interceptors, guards, list and form base components. | 1.5 |

Done when: M1 demo passes; automated test proves two tenants are isolated.

### Phase 2 - Masters and Charges (W10-W15, 6 weeks)

| Sub-module | How to build | Weeks |
| --- | --- | --- |
| Departments, specimen types, units, organisms, hospitals, suppliers, promoters | Generic master CRUD pattern (one reusable Angular list-and-form component and one API pattern) so each master takes about one day | 1 |
| Tests | Test form, parameters grid, ranges by sex/age/range, formulas, copy test, active toggle, inline sort order | 2.5 |
| Test templates | Rich-text templates for narrative tests | 0.5 |
| Packages | Package builder with tests and price | 1 |
| Charges and price lists | Charges grid (default, B2B, extra price lists), corporate-wise charges, copy charges, import/export | 1.5 |
| Referral doctors, centers, corporates, outsource labs | Forms, center print settings and images, corporate to price list mapping, outsource charges | 1.5 (overlaps) |

Done when: a tenant can build its full test catalog and price lists, with Excel import working.

### Phase 3 - Registration, Billing and Patient Search (W14-W19, 6 weeks)

| Sub-module | How to build | Weeks |
| --- | --- | --- |
| Number series and pricing resolver | Transactional number generation; price lookup by corporate or center | 1 |
| Registration | Config-driven form, patient and doctor quick-add, test picker with departments and packages tabs, order list, money block, receipt print | 2.5 |
| Billing and payments | Discount rules by role, payment modes, balance, collect later, receipts, refunds, delete with reason and log | 1.5 |
| Patient search | Status cards, filters, grid, view drawer with collect-now, edit modal, add test, barcode scan search | 1.5 |

Done when: M2 criteria pass, and registration with three tests takes under 60 seconds in a usability test.

### Phase 4 - Sample Flow and Results (W18-W24, 7 weeks)

| Sub-module | How to build | Weeks |
| --- | --- | --- |
| Sample tracking | Sample records per booking test, barcode labels, receive and reject, status engine with configurable names and colors | 1.5 |
| Result dashboard | Status counters, colored grid, filters, bulk actions framework | 1.5 |
| Result entry | Parameter grid, auto ranges and flags, formulas, delta, comments, hold/reject, abnormal side panel, narrative templates | 2.5 |
| Authorization | Provisional, pre-auth, authenticated flow by permission, amendment versions, critical alerts | 1.5 |

Done when: results can be entered, flagged and authorized with full audit and permission checks.

### Phase 5 - Reports, Delivery and Signatures (W23-W27, 5 weeks)

| Sub-module | How to build | Weeks |
| --- | --- | --- |
| Report PDF engine | Template-driven PDF per center: header images, margins, fonts, sections, ranges, flags, QR; letterhead on or off; split by category | 2 |
| Signatures | Signature master, image upload with crop and enhance, validity window, selection rules | 1 |
| Delivery | Email, WhatsApp and SMS templates and queue, bulk send from result dashboard, delivery log, block-if-due rule | 1.5 |
| Print settings screens | Auto-generated from config groups | 0.5 |

Done when: M3 MVP criteria pass.

### Phase 6 - Referral, Corporates, Outsource, Complement (W24-W27, 4 weeks)

| Sub-module | How to build | Weeks |
| --- | --- | --- |
| Complement engine | Rules by doctor, test, promoter; basis from config (total, paid, cost to lab) | 1.5 |
| Outsource workflow | Send, receive, track, attach result, cost price | 1.5 |
| Corporate and center scoping | Data visibility rules, settlement basics | 1 |

### Phase 7 - Dashboard and Reports (W27-W31, 5 weeks)

| Sub-module | How to build | Weeks |
| --- | --- | --- |
| Dashboard | Widgets from config, summary queries, work queue, birthdays, announcements | 1 |
| Report framework | One reusable report definition (filters, columns, query, export) so each report is mostly configuration | 1 |
| MIS and cost reports | Daily collection, payments, complement reports, cost vs revenue | 1.5 |
| Other reports | TAT, worksheets, logs, discount, rejection, critical value, summaries | 1.5 |

### Phase 8 - Machine Integration (W28-W31, 4 weeks)

| Sub-module | How to build | Weeks |
| --- | --- | --- |
| Machine and code mapping | Machine master, parameter to machine code mapping screens | 1 |
| Bridge service | Small Windows/Linux service that reads serial, TCP, HL7/ASTM or files and posts to the API with a tenant key | 2 |
| Machine data screen and auto-fill | Raw data viewer, parsing, mapping, exceptions, Interfaced status | 1 |

### Phase 9 - SaaS Admin (W32-W35, 4 weeks)

| Sub-module | How to build | Weeks |
| --- | --- | --- |
| Plans and limits | Plan CRUD, enforcement middleware, usage counters | 1.5 |
| Subscriptions and invoices | Subscription lifecycle, reminders, invoices, optional online payment | 1.5 |
| Tenant console and help center | Tenant list, health, announcements, user manual editor with images | 1 |

### Phase 10 - Hardening and Go-live (W36-W40, 5 weeks)

| Step | Work |
| --- | --- |
| Performance | Load test with large tenants, index tuning, caching review |
| Security | Penetration test, tenant-isolation tests, secrets review |
| UAT | Two to three pilot labs use it in parallel with their current system |
| Data import | Excel and CSV importers for tests, charges, doctors, patients |
| Operations | Backup and restore drill, monitoring, alerts, runbooks |
| Documentation | Admin guide, user manual with screenshots, API docs |
| Go-live | Staged tenant onboarding, hyper-care support for 2 weeks |

## 5. Parallel Tracks

| Track | Runs through | Notes |
| --- | --- | --- |
| QA automation | W5 onward | API tests per module, Playwright end-to-end for critical flows, tenant isolation tests in every build |
| UX refinement | W10 onward | Designer reviews each built screen against the prototype |
| DevOps | W1 onward | CI/CD, environments, infrastructure as code, monitoring |
| Documentation | W20 onward | User manual pages written as each module closes |

## 6. Definition of Done (Each Module)

- Acceptance criteria in the FRS pass.

- Unit tests for business rules; API integration tests green.

- Permission keys defined and seeded; unauthorized access returns 403.

- Config keys registered for anything tenant-variable.

- Audit entries written for changes.

- UI matches the design system and works on desktop and tablet.

- Migration scripts apply cleanly to a fresh tenant and to an existing tenant.

- Help page drafted.

## 7. Effort Summary (Approximate)

| Module group | Person-weeks |
| --- | --- |
| Discovery and design | 12 |
| Platform foundation | 36 |
| Masters and charges | 30 |
| Registration and billing | 28 |
| Sample and results | 32 |
| Reports, delivery, signatures | 22 |
| Referral, corporates, outsource | 16 |
| Dashboard and reports | 22 |
| Machine integration | 14 |
| SaaS admin | 16 |
| Hardening and go-live | 24 |
| Total | about 252 person-weeks |

With a team of 6 to 7 engineers and a designer, this fits the 40-week plan; a smaller team lengthens the timeline roughly in proportion.

## 8. Risks to the Timeline

| Risk | Impact | Response |
| --- | --- | --- |
| Late changes to test and report formats | Rework in Phases 2 to 5 | Freeze report layouts at W12 and use the config-driven template engine |
| Machine protocol surprises | Phase 8 delay | Get sample outputs from target machines by W10 |
| Tenant migration failures | Release risk | Canary tenants first; automated rollback scripts |
| Pilot lab availability for UAT | Phase 10 delay | Sign pilot labs by W20 |
| Team capacity | Overall delay | Use the 4-week buffer; protect MVP scope |

## 9. Next Steps

- Confirm team size and start date so the weeks above become calendar dates.

- Approve the phase order, especially MVP at W27.

- Share target machine models and priority integrations.

- Decide SaaS pricing model so Phase 9 can be finalized.